## TC_StudyHistory
Test Case ID |  | TC_StudyHistory | Test Case Description | Verify admin/PM can access change history for a study
Created By |  | Dan Miller | Reviewed By | Lucy Chung |  | Version |  | 1.1
QA Tester’s Log |  | As admin/PM, I should be able to access study history
Tester's Name |  | Dan Miller | Date Tested | 2021-03-23 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User id without admin access |  |  | 1 | N/A
2 | User id with admin access |  |  | 2
3 | At least one study in system |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | As non-admin, navigate to http://127.0.0.1:8000/KITS/ and select 'Studies' |  | KITS Studies page is displayed | As Expected |  |  | Pass
2 | Select edit for an existing study |  | KITS Edit Study page is displayed | As Expected |  |  | Pass
3 | Change comment field to 'THIS IS A TEST' and select update |  | System returrns to KITS Studies page | As Expected |  |  | Pass
4 | Select edit for the study again and verify that the comment was updated. |  | System display KITS Edit page with comment updated. | As Expected |  |  | Pass
5 | Login to admin site as admin/PM |  | System will display Site Admin page | As Expected |  |  | Pass
6 | Click on the 'Studys' linke |  | System will display the list of studies | As Expected |  |  | Pass
7 | Select the study that has been edited |  | System will display the Change Study page with study details | As Expected |  |  | Pass
8 | Select the History button |  | System will display the study change history | As Expected |  |  | Pass
9 | Select the previous history entry and click on revert |  | System will update study to the previous verion. | As Expected |  |  | Pass
10
11
12
13

## TC_KitInstanceHistory
Test Case ID |  | TC_KitInstanceHistory | Test Case Description | Verify users can access list of all changes to kit instances
Created By |  | Dan Miller | Reviewed By | Lucy Chung |  | Version |  | 1.1
QA Tester’s Log |  | As user, I should be able to access a list showing all changes to all kit instances
Tester's Name |  | Dan Miller | Date Tested | 2021-04-14 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User id without admin access |  |  | 1 | N/A
2 | At least one study in system |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | As non-admin, navigate to http://127.0.0.1:8000/KITS/ and select 'Studies' |  | KITS Studies page is displayed | As Expected |  |  | Pass
2 | Note a study name from the list; select Check In Kits |  | KITS Kit Type List page is displayed | As Expected |  |  | Pass
3 | Select IRB Number of previosly noted study |  | System returrns row with the study (blank if no KIT types assigned) | As Expected |  |  | Pass
4 | Select Add Kit Type, complete the Add Kit Type form and click Add |  | System displays KITS Kit Type List updated. | As Expected |  |  | Pass
5 | Select Add Kit Instance for the added type |  | System will display Adding a kit form | As Expected |  |  | Pass
6 | Complete the add kit instance form and click submt |  | System will display the list of Types of Kits | As Expected |  |  | Pass
7 | Select the Studies link in the menu, then select the study that kit was added to |  | System will display the Study Detail page | As Expected |  |  | Pass
8 | Select the See all Kits in inventory button |  | System will display All Kits In Inventory with new Kit Instance | As Expected |  |  | Pass
9 | Select Kit Instance Changes from the menu |  | System will show the instance id of added kit instances with status, expiration, user id, action, and date/time | As Expected |  |  | Pass
10
11
12
13

## TC_AddKitOrderInfo
Test Case ID |  | TC_AddKitOrderInfo | Test Case Description | Verify that a user can add kit information to a study
Created By |  | Lucy Chung | Reviewed By |  |  | Version |  | 1.0
QA Tester’s Log |  | As a user, I should be able to add kit order information
Tester's Name |  | Lucy Chung | Date Tested | 2021-04-07 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User ID and password |  |  | 1 | One study in KITS system, configured in any manner
2 | Network connection |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate to 127.0.0.1:8000 |  | KITS home page is displayed | As Expected |  |  | Pass
2 | Click 'Log In' (if not already logged in) and enter user credentials |  | KITS home page is displayed again with logged in user in navbar | As Expected |  |  | Pass
3 | Click 'Studies' |  | KITS study list page is displayed | As Expected |  |  | Pass
4 | Click 'View Details' on one of the created studies |  | KITS study detail page for respective study is displayed | As Expected |  |  | Pass
5 | Click 'Add Kit Order Info' button |  | Form to add kit order info is displayed | As Expected |  |  | Pass
6 | Choose respective study, choose kit order type, enter respective type, enter description (optional) |  | Fields will be filled with respective info | As Expected |  |  | Pass
7 | Click 'Confirm' |  | KITS study detail page for respective study is displayed, now with kit order information | As Expected |  |  | Pass

## TC_EditKitOrderInfo
Test Case ID |  | TC_EditKitOrderInfo | Test Case Description | Verify that a user can update kit order information for a study
Created By |  | Lucy Chung | Reviewed By |  |  | Version |  | 1.0
QA Tester’s Log |  | As a user, I should be able to update kit order information for studies that are ready to open or have opened
Tester's Name |  | Lucy Chung | Date Tested | 2021-04-07 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User ID and password |  |  | 1 | One study in KITS system, configured in any manner
2 | Network connection |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate to 127.0.0.1:8000 |  | KITS home page is displayed | As Expected |  |  | Pass
2 | Click 'Log In' (if not already logged in) and enter user credentials |  | KITS home page is displayed again with logged in user in navbar | As Expected |  |  | Pass
3 | Click 'Studies' |  | KITS study list page is displayed | As Expected |  |  | Pass
4 | Click 'View Details' on one of the created studies |  | KITS study detail page for respective study is displayed | As Expected |  |  | Pass
5 | Click 'Edit Kit Order Info' button |  | Form to edit kit order info is displayed | As Expected |  |  | Pass
6 | Choose respective study, choose kit order type, enter respective type, enter description (optional) |  | Fields will be filled with respective info | As Expected |  |  | Pass
7 | Click 'Confirm' |  | KITS study detail page for respective study is displayed, now with updated kit order information | As Expected |  |  | Pass

## TC_AddReqInfo
Test Case ID |  | TC_AddReqInfo | Test Case Description | Verify that a user can add requisition sheet information to a study
Created By |  | Cameron Rippey | Reviewed By |  |  | Version |  | 1.0
QA Tester’s Log |  | As a user, I should be able to add requisition sheet information
Tester's Name |  | Cameron Rippey | Date Tested | 2021-04-07 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User ID and password |  |  | 1 | One study in KITS system, configured in any manner
2 | Network connection |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate to 127.0.0.1:8000 |  | KITS home page is displayed | As Expected |  |  | Pass
2 | Click 'Log In' (if not already logged in) and enter user credentials |  | KITS home page is displayed again with logged in user in navbar | As Expected |  |  | Pass
3 | Click 'Studies' |  | KITS study list page is displayed | As Expected |  |  | Pass
4 | Click 'View Details' on one of the created studies |  | KITS study detail page for respective study is displayed | As Expected |  |  | Pass
5 | Click 'Add Requisition Info' button |  | Form to add requisition info is displayed | As Expected |  |  | Pass
6 | Choose respective study, choose requisition type, enter respective type, enter description (optional) |  | Fields will be filled with respective info | As Expected |  |  | Pass
7 | Click 'Confirm' |  | KITS study detail page for respective study is displayed, now with appropriate requisition sheet information | As Expected |  |  | Pass

## TC_EditReqInfo
Test Case ID |  | TC_EditReqInfo | Test Case Description | Verify that a user can update requisition sheet information for a study
Created By |  | Cameron Rippey | Reviewed By |  |  | Version |  | 1.0
QA Tester’s Log |  | As a user, I should be able to update requisition sheet information for studies that are ready to open or have opened
Tester's Name |  | Cameron Rippey | Date Tested | 2021-04-07 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User ID and password |  |  | 1 | One study in KITS system, configured in any manner
2 | Network connection |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate to 127.0.0.1:8000 |  | KITS home page is displayed | As Expected |  |  | Pass
2 | Click 'Log In' (if not already logged in) and enter user credentials |  | KITS home page is displayed again with logged in user in navbar | As Expected |  |  | Pass
3 | Click 'Studies' |  | KITS study list page is displayed | As Expected |  |  | Pass
4 | Click 'View Details' on one of the created studies |  | KITS study detail page for respective study is displayed | As Expected |  |  | Pass
5 | Click 'Edit Requisition Info' button |  | Form to edit requisition info is displayed | As Expected |  |  | Pass
6 | Choose respective study, choose requisition type, enter respective type, enter description (optional) |  | Fields will be filled with respective info | As Expected |  |  | Pass
7 | Click 'Confirm' |  | KITS study detail page for respective study is displayed, now with updated requisition sheet information | As Expected |  |  | Pass

## TC_UserHistory
Test Case ID |  | TC_UserHistory | Test Case Description | Verify user history tracked while changing objects
Created By |  | Dan Miller | Reviewed By | Lucy Chung |  | Version |  | 1.1
QA Tester’s Log |  | Ensure non-admin change to study, order history, kit, kit instance etc tracked
Tester's Name |  | Dan Miller | Date Tested | 2021-03-29 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User id without admin access |  |  | 1 | N/A
2 | User id with admin access |  |  | 2
3 | At least one study in system |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | As non-admin, navigate to http://127.0.0.1:8000/KITS/ and select 'Studies' |  | KITS Studies page is displayed | As Expected |  |  | Pass
2 | Select edit for an existing study |  | KITS Edit Study page is displayed | As Expected |  |  | Pass
3 | Change comment field to 'THIS IS A TEST' and select update |  | System returrns to KITS Studies page | As Expected |  |  | Pass
4 | Login to admin site as admin/PM |  | System will display Admin Home paage | As Expected |  |  | Pass
5 | Click on the UserHistory Link |  | System will display UserHistory page | As Expected |  |  | Pass
6 | Note that most recent user history displayed is for the non-admin user that made the edit to 'study' |  | UserHistory includes user id of most recent user to make a change | As Expected |  |  | Pass
7 | Note that object change is correctly displayed |  | UserHistory includes the Study object details for the changed object | As Expected |  |  | Pass
8
9
10
11
12
13

## TC_study_list_and_details
Test Case ID |  | TC_study_list_and_details | Test Case Description | User navigates to Studies tab, able to search for study by IRB number, pet name, or status and review the details of the specific study they look up
Created By |  | Lucy Chung | Reviewed By | Dan Miller |  | Version |  | 1.1
QA Tester’s Log
Tester's Name |  |  | Date Tested | 2021-03-08 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User is able to log into KITS |  |  | 1 | N/A
2 | Studies are present in the data base |  |  | 2
3 | Kits associated with each kit are present in the database |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | User navigates from home tab to studies tab |  | User will be redirected to studies_list page | As Expected |  |  | Pass
2 | User searches for a study by IRB number for an exisiting study and presses 'enter' |  | Studies_list page will repopulate the page with the study that matches that IRB number | As Expected |  |  | Pass
3 | User searches for a study by pet name for an exisiting study and presses 'enter' |  | Studies_list page will repopulate the page with the study that matches that pet name | As Expected |  |  | Pass
4 | User filters the studies by status |  | Studies_list page will repopulate the page with studies that matches the status | As Expected |  |  | Pass
5 | After user finds the specific study, they click on 'View Details' |  | User is redirected to study_detail page specific for the study they cllicked 'View Details' on. | As Expected |  |  | Pass
6
7
8
9
10
11
12
13
14

## TC_EditStudy
Test Case ID |  | TC_EditStudy | Test Case Description | Verify that a user can edit details of a study and archive (thus closing) an open study.
Created By |  | Cameron Rippey | Reviewed By | Dan Miller |  | Version |  | 1.0
QA Tester’s Log |  | As a user, I should be able to update the study status or close (thus archiving) the study.
Tester's Name |  | Cameron Rippey | Date Tested | 2021-03-09 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Internet Connection |  |  | 1 | Test Study created
2 | User account for KITS application |  |  | 2
3 | PythonAnywhere Deployment Link |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate to 127.0.0.1:8000/KITS/ |  | Site will display KITS home page | As Expected |  |  | Pass
2 | Click the green 'Login' button |  | Site will display login form with fields for username and password, login button, and forgot password button | As Expected |  |  | Pass
3 | Enter username and newly-changed password |  | Fields for username and password should be filled | As Expected |  |  | Pass
4 | Click 'Log In' |  | Site will display home page of KITS application | As Expected |  |  | Pass
5 | Click 'Studies' |  | Site will display list of studies available | As Expected |  |  | Pass
6 | Click 'Edit' for any study |  | Site will display form for editing the details of the selected study | As Expected |  |  | Pass
7 | Edit 'Kit Order' field |  | Dropdown to select 'Kit Order' choices will display | As Expected |  |  | Pass
8 | Edit 'IRB Number' field |  | Field to enter IRB Number should populate | As Expected |  |  | Pass
9 | Edit 'Pet Name' field |  | Field to enter Pet Name should populate | As Expected |  |  | Pass
10 | Edit 'Comment' field |  | Field to enter Comment should populate | As Expected |  |  | Pass
11 | Edit 'Sponsor Name' field |  | Field to enter Sponsor Name should populate | As Expected |  |  | Pass
12 | Edit 'Requisition Form Qty' field |  | Field to enter Requisition Form Qty should populate | As Expected |  |  | Pass
13 | Edit 'Status' field |  | Dropdown to select Status should display | As Expected |  |  | Pass
14 | Edit 'Start Date' field |  | Field to enter Start Date should populate | As Expected |  |  | Pass
15 | Edit 'End Date' field |  | Field to enter End Date should populate | As Expected |  |  | Pass
16 | Click 'Update' |  | Site should display study list with updated details for selected study | As Expected |  |  | Pass
17 | Click 'Archive' for any study |  | Site should display confirmation dialog for archiving the study, identified by pet name | As Expected |  |  | Pass
18 | Click 'OK' |  | Site should display study list with selected study status set to 'Closed' | As Expected |  |  | Pass

## TC_Reports_ExpiredKits
Test Case ID |  | TC_UserHistory | Test Case Description | Verify user history tracked while changing objects
Created By |  | Lucy Chung | Reviewed By | Lucy Chung |  | Version |  | 1.1
QA Tester’s Log |  | Ensure non-admin change to study, order history, kit, kit instance etc tracked
Tester's Name |  | Lucy Chung | Date Tested | 2021-03-29 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User id without admin access |  |  | 1 | N/A
2 | User id with admin access |  |  | 2
3 | Inventory contains expired kits |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | As non-admin, navigate to http://127.0.0.1:8000/KITS/ and select 'Reports' |  | KITS Reports page is displayed | As Expected |  |  | Pass
2 | Select 'Expired Reports' |  | KITS Expired Reports is displayed and shows all expired kits from all studies | As Expected |  |  | Pass

## TC_AddKit
Test Case ID |  | TC_AddKit | Test Case Description | Verify that user can add a kit and the database will be updated
Created By |  | Steven Press | Reviewed By | Lucy Chung |  | Version |  | 1.1
QA Tester’s Log |  | As a user, I should be able to add a kit
Tester's Name |  | Steven Press | Date Tested | 2021-03-09 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User is logged in |  |  | 1 | N/A
2 | User is authorized to add a kit |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate directly to 127.0.0.1:8000/KITS/kit_list |  | The system displays the KITS Kit page | As Expected |  |  | Pass
2 | Select "Check-in Kit" |  | System will display the "Check-in Kit" form at http://127.0.0.1:8000/KITS/kit_list/kit_checkin/ | As Expected |  |  | Pass
3 | Complete the create Check-in Kit form and press "Add" |  | Be navigated back to http://127.0.0.1:8000/KITS/kit_list/ | As Expected |  |  | Pass
4
5
6
7
8
9
10
11
12
13

## TC_checkout
Test Case ID |  | TC_checkout | Test Case Description | Verify that user can check a kit out or demolish a kit and the database will update and display properly
Created By |  | Steven Press | Reviewed By | Steven Press |  | Version |  | 1.1
QA Tester’s Log |  | As a user, I should be able to check a kit out
Tester's Name |  | Steven Press | Date Tested | 2021-04-06 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | User is logged in |  |  | 1 | N/A
2 | User is authorized to check a kit out |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Navigate directly to 127.0.0.1:8000/KITS/kit_checkout |  | The system displays the KITS Checkout Page | As Expected |  |  | Pass
2 | Select Checkout/Demolish kit |  | System will display a checkout/demolish confirmation form with its respective status | As Expected |  |  | Pass
3 | Select Checkout/Demolish button |  | Be navigated back to http://127.0.0.1:8000/KITS/kit_checkout and the respective kit will change its status to checked-out or demolished | As Expected |  |  | Pass
4
5
6
7
8
9
10
11
12
13